# Mid-Term Review: Valdora District Health Strengthening Programme

TEST DOCUMENT. This report is entirely made up for testing Report Harmonizer. All names, places, organisations and figures are fictional.

# 1. Introduction

The Ministry of Health of the fictional Republic of Valdora commissioned this review to assess, at the programme's midpoint, how far the Valdora District Health Strengthening Programme (VDHSP) has progressed towards its stated objectives. These were set out in the original programme document of March 2023 and revised in January 2024.

The review team of three independent consultants conducted fieldwork in four of the seven programme districts between 12 and 28 May 2026. The team held 46 key informant interviews and 9 focus group discussions with health staff, district officials and community representatives.

# 2. Findings

Training went well, and staff liked it. The programme trained 312 health workers against a target of 300. This is more than planned, which is good. However, some of them left their posts soon after.

Drug stockouts are still a big problem. In Korvan district, 7 out of 11 clinics had no amoxicillin at the time of our visit. Staff said this happens often. The supply chain is not working yet.

The district health officer in Korvan, Dr. Amina Telo, told us, "We order on time, but the trucks come when they come." This matches what we saw in the records.

Preliminary evidence suggests that the introduction of monthly supervision visits may have contributed to a modest improvement in the completeness of facility reporting, However, it remains unclear whether this is due to the programme or to the parallel national digitisation initiative.

Maternal health indicators appear to show a positive trend, with the proportion of facility-based deliveries in the four visited districts having increased from 58 percent in 2023 to 64 percent in 2025. However, data quality concerns mean these figures should be interpreted with caution.

The budget situation is mixed. By April 2026, 71 percent of the allocated funds (EUR 4.2 million out of EUR 5.9 million) had been disbursed, which is broadly in line with the workplan. However, spending on the community component has lagged considerably behind.

# 3. Recommendations

The programme management unit should work closely with the Central Medical Stores to review last-mile distribution arrangements in full and identify the main bottlenecks.

Staff retention needs fixing, as trained staff leave. The programme should look at incentives, maybe housing or allowances, and consult the districts about it before the next training round starts.

The programme might consider aligning its reporting tools with the national digital system. This could potentially reduce the double reporting burden currently experienced by facility staff.

Finally, the review team would like to thank all those who gave their time to participate in interviews and discussions, and in particular the staff of the four district health offices visited.